## Sheet2
Integrated Transport Schemes Programme 2024-25
Scheme Type | District | Scheme Name and Location | Scheme Description | Anticipated Delivery (Spring/Summer/Autumn/Winter) | Scheme Status
Targeted Local Safety Schemes | SBC | Holdiford Road bridges, Milford | Following feasibility and consultation, traffic signals will be installed at the canal and river bridges on Holdiford Road were there is restricted width and intervisibility. | Spring | Construction
Targeted Local Safety Schemes | SMDC | A53 Buxton Road, between Blackshaw Moor and Flash | Scheme following feasibility study includes a speed limit reduction to 50mph, marker posts at side road junctions and blind spots, warning signs to alert drivers to expect slower vehicles existing the layby near Brown Lane, traffic island at Blackmere Road/Hazel Barrow Lane junction and updated warning and directional signage along the route. | Winter | Design
Targeted Local Safety Schemes | ESBC | B5030 Ashbourne Road, between Uttoxeter and Rocester | The preferred option in the feasibility study includes, central hatching reducing the likelihood of vehicles crossing onto the path of oncoming vehicles, potential for double white lines in narrower places to prevent overtaking, junction aheads signs, maintenance of vegetation and a speed limit reduction within the National Speed Limit stretch to 50MPH. | Winter | Design
Targeted Local Safety Schemes | ESBC | Loxley crossroads, Kingstone, Uttoxeter | To improve safety, it is recommended that the two side roads are offset to give better sight of the junction. | Autumn/Winter | Design
Targeted Local Safety Schemes | County wide | Additional Local Safety Schemes | New accident cluster locations identified following data analysis. | All Year | Ongoing
Targeted Local Safety Schemes | CCDC/ ESBC | Vehicle Activated Signs (VAS) | The installation of two VAS signs are proposed for installation to help reduce casualties at Rugeley Road near to Caravan Park, Beaudesert, Cannock Chase and Forest Road near to Junction of Dunstall Cross / Dunstall Hill, Rangemore Hill. | Autumn | Design
Community Liaison Schemes | SMDC | Leek Road junction with A53 Buxton Road realignment and improvement | Revised junction layout to slow vehicle manoeuvres and VAS and general improvements to lining and signing. | Spring | Construction
Community Liaison Schemes | ESBC | Violet Way, Burton Upon Trent | The scheme will replace the existing speed cushions with full width road humps as well as provide the required road surfacing and road markings. | Summer | Tender
Community Liaison Schemes | SBC | Brocton Road, Stafford | The feasibility study recommends the implementation of a weight restriction long Brocton Road to Sawpit Lane as well as signage and road marking mprovements on the bend outside Dora Rose Care Home. There is funding committed from DHP of £6k. | Summer | Tender
Community Liaison Schemes | TBC | Flood mitigation at Glascote arches, Tamworth | A feasibility study recommended options for mitigating the flooding and the preferred short term low cost option that will be delivered in 2024/25 is to flush through the drains and put a camera down. | Autumn | Design
Community Liaison Schemes | ESBC | Uttoxeter Parking Review - Market Place, Uttoxeter | Proposals include increasing on-street parking and disabled bays, changes to on-street timings and cycle parking. On-street electric vehicle charging points will be considered through other funding opportunities in line with the EV Strategy. | TBC | Design
Community Liaison Schemes | ESBC | Traffic management Back Lane, Uttoxeter | Enforcement and engineering solutions to deter through traffic along Back Lane. Future proposals could include a bus gate that could potentially be enforced by ANPR cameras. | TBC | Design
Community Liaison Schemes | ESBC | Uttoxeter town centre bollard enforcement | Reinstatement of a rising bollard at the north end of High Street, Uttoxeter. | Autumn | Design
Community Liaison Schemes | ESBC | Stone Road/Smithfield Road Junction improvement, Uttoxeter | Measures to improve pedestrian environment at a key junction providing access to local schools. Scheme includes amending the alignment of an existing zebra crossing, improved signage and lining, guardrail upgrade and introduction of a TRO to prohibit unsafe parking which limits visibility. | TBC | Design
Community Liaison Schemes | SSDC | Codsall Road, Dam Mill Codsall | Implementation of measures to reduce speeds and improve safety at a bend in Codsall Road. | Summer | Design
Community Liaison Schemes | LDC | A51/ Hood Lane Weight Limit Signage, Rugeley | Installation of two advanced weight limit signs on the A51 on the approach to Hood Lane (in both directions) advising HGVs of the 7.5t weight limit. | Autumn | Design
Community Liaison Schemes | ESBC | Belvedere Road traffic management, Burton upon Trent | The proposal includes the review of central hatching, edge of carriageway markings, markings to reduce the size of the bell mouth junction on Outwoods Street and a relocation of the bus stop. | Autumn | Design
Community Liaison Schemes | SBC | A519 Beech Road Safety Improvements | Following the outcome of a feasibility study, the preferred option is likely to include the upgrading of existing warning signage and providing changes to the speed limit at the bend in the road. | Autumn | Design
Community Liaison Schemes | SBC | A513 Lichfield Road, Shugborough Speed Limit Change | The proposal is to reduce the speed limit from 60mph to 40mph, tying in with the existing 40mph in Milford. This section of road includes entrances/exits to Shughborough and Cannock Chase punch bowl car park that both have visibility restrictions due to the bends in the road. | Autumn | Design
Community Liaison Schemes | LDC | A513 Kings Bromley Lane traffic management | A feasibility study has been completed and the preferred option is to deliver additional advanced traffic signs, bollards within the verge and additional road marking on the approaches to the junction. | Summer/Autumn | Design
Community Liaison Schemes | SMDC | High Street Cheadle, enhanced vehicle access to local businesses | The proposal is to add short-stay parking bays and loading bays to further support the local businesses in the area. The Traffic Regulation Order (TRO) will be amended before relining, following recent re-surfacing works. | Spring | Construction
Community Liaison Schemes | ESBC | B5013/B5014 Uttoxeter Road junction improvement, Abbots Bromley | The proposal includes signage improvements and speed control measures on the approaches to the junction. | Winter | Design
Countywide Commitments | County wide | Divisional Highway Programme | The Divisional Highway Programme is a Local Member Initiative that helps to fund highway and transport schemes prioritised by County Councillors, such as pedestrian safety, safety and congestion issues at local junctions, school traffic, HGV routing, speeding through villages, parking issues and rat-running on inappropriate roads. | All Year | Ongoing
Countywide Commitments | County wide | Rights of Way Maintenance and Improvements | Delivery of a programme of maintenance and improvements to the PRoW network to address issues and increase efficiency of management. Schemes in 23/24 will focus on: • Major PRoW improvement schemes • 'Finding Your Way' Programme • 'Miles without Stiles' Programme • Community Paths Initiative • Path Volunteer Programme | All Year | Ongoing
Countywide Commitments | County wide | Local Safety Scheme: Targeted wet road skidding sites | A route that has a wet road collision problem occurring predominantly at junctions and/or bends and approaches to roundabouts will be targeted via the Wet Roads Programme. | All Year | Ongoing
Countywide Commitments | County wide | Local Safety Schemes: Mass Action Programme | The Mass Action programme is a means to address a number of common type collisions that, while potentially occurring across a wide area, have a common cause, theme or pattern. The works involve the use of known engineering solutions to negate the actual hazards notably via signage and lining improvements. | All Year | Ongoing
Countywide Commitments | County wide | Bus stop Infrastructure improvement programme | A programme of works to improve the County Council’s bus stop infrastructure to provide a more attractive environment for bus users ensuring a consistent standard. | All Year | Ongoing
Transport Strategy Schemes | ESBC | B5017 Corridor Improvements, Burton | Deliver traffic management and pedestrian improvements on the B5017 between Wellington Road/Shobnall Road and Postern Road, taking into account local community concerns, safety concerns around Shobnall Primary School and access to the hospital. | Winter/Spring | Consultation
Transport Strategy Schemes | ESBC | Transport improvements associated with Land South of Branston, Burton | Detailed designs will be progressed in line with the outcome of public consultations that were completed in 2023 on walking and cycling proposals along the B5018 corridor, between Main Street Branston and Paget High School. It is currently expected that the scheme will be delivered in 2025/26. | ongoing | Design
Transport Strategy Schemes | SBC | A34 Stafford Road / Eccleshall Road junction, Stone | Investigation and design of improvement options to provide additional vehicular capacity and walking and cycling provision on the Eccleshall Road approach to Walton Island. | Summer | Design
Transport Strategy Schemes | LDC | Eastern Avenue pedestrian and cycle provision between A51 junction and Dimbles Lane, Lichfield. | Review of pedestrian provision at the A51 junction and cycle and footway provision connecting to Grange Lane south of Eastern Avenue and to existing footpaths that connect to Dimbles Lane. Shared/segregated cycle use needs to be provided along the northern side of the road serving The Friary School and Friary Grange Leisure Centre, with cycling provision at all crossings to connect to residential areas to the south of Eastern Avenue. The A51 junction needs to be reviewed in terms of HGV movements. There are significant drainage issues on footways in the vicinity of the narrow footways adjacent to the school entrance. | TBC | Design
Transport Strategy Schemes | LDC | Abnalls Lane (A51 Lichfield to Burntwood) | Public consultation has been completed on scheme options. The preferred option has been amended to take account the outcome consultation. The final scheme will focus on providing a safer crossing point on the A51, to be delivered in 2024/25 | Summer | Design
Transport Strategy Schemes | TBC | Amington Cycle Route and School Street, Tamworth | Detailed design and consultations will be completed and the final scheme is programmed to be delivered during July and August 2024. The scheme delivers walking and cycling improvements between the High School, along Florendine Street where the local primary school is situated, across the busy Tamworth Road, linking to the canal to the towpath and the wider residential areas beyond the canal. | Summer/Autumn | Design
Transport Strategy Schemes | EBC | Shobnall Road, Burton upon Trent National Cycle Network | Installation of LTN1/20 compliant cycling infrastructure along Shobnall Road Burton upon Trent to link National Cycle Network route 54 from the access to Shobnall Fields with Anglesey Street, including installation of National Cycle Network signage. | Autumn | Design
Transport Strategy Schemes | NBC | Newcastle-under-Lyme Town Centre Permeability Project | Detailed design, consultation and the delivery of pedestrian and cycle improvements connecting the new cycle infrastructure on George Street with the town centre. The proposal includes cycle provision along Hassell Street, improved public realm and crossing provision at the Hassell Street/Barrack's Road junction and improved provision along Barrack's Road linking to the Civic centre. | Autumn | Design
Transport Strategy Schemes | EBC | Burton upon Trent Cycle Network Enhancements | Cycling and pedestrian improvements will be delivered along Borough Road between the rail station and the town hall; along connecting roads through residential areas, together with improved cycle provision on the A511. | Winter | Tender
Transport Strategy Schemes | ESBC, SBC, TBC, CCC, NBC | Cycle Parking | Design of high quality cycle parking at key locations in Burton, Stafford, Newcastle, Cannock and Tamworth to support the new segregated cycle routes being delivered as part of Active Travel Funds. | ongoing | Design
Transport Strategy Schemes | NBC | Newcastle Greenway barrier redesign | Silverdale greenway runs 2.7miles and is part of the National Cycle Network. A feasibility study has been produced by Sustrans that identifies how the barriers could be re-designed to ensure they meet Equalties Act 2010 requirements. Funding in 204/25 will be used to deliver the first phase of improvements that have received support from local communties and stakeholders. | Summer (phase 1) | Design
Transport Strategy Schemes | LDC | Birmingham Road / A51 / St John Street junction improvement, Lichfield | Feasibility, appraisal of potential options and detailed design of the preferred option to enhanced pedestrian and cycle facilities at the Birmingham Road / A51 / St John Street signalised junction, potentially including cycle and pedestrian phases, refuges and reduced crossing distances. Scheme delivery will be in a future year, as resources permit. | TBC | Design
Transport Strategy Schemes | LDC | Cycling and walking enhancement between St John Street and Burton Old Road, Lichfield. | Feasibility, appraisal of potential options and detailed design of walking and cycling improvement along Birmingham Road between St John Street and Burton Old Road. | TBC | Design
Transport Strategy Schemes | ESBC | Uttoxeter Rail Station Bridge/ Underpass lighting improvement | To light the vital link from the train station to Uttoxeter Town Centre Waitrose to improve connectivity. | TBC | Design
Transport Strategy Schemes | LDC | Fradley Active Travel improvements | Design and deliver improvements to active travel modes to provide connections to key local infrastructure and services into the Fradley Park/Halifax Avenue housing development. | Autumn | Design
Transport Strategy Schemes | ESBC | Safe Walking and Wheeling along A5121 corridor, Burton | Detailed design, consultaition and delivery of walking and wheeling improvementsa long A5121 Derby Street, including side road junction treatments, enhanced footways and safer crossing facilities. | Autumn | Design
Transport Strategy Schemes | NBC | Active Travel - A52 George Street, Newcastle | Footway enhancements following completion of recent cycle infrastructure scheme | Summer | Design
Transport Strategy Schemes | CCDC | Active Travel - Lichfield Road, Cannock | Pedestrian Crossing amendments following completion of recent cycle infrastructure scheme | Spring | Construction