## Programme
Programme Name: |  |  | Carriageway Preventative Treatments - Pre-Patching Operations
Programme Reporting Period: |  |  | March 2024 - March 2025
* All programmes of work are correct at the time of issuing. Deliverables and timeframes may be subject to change.
Road No. | Unique Street Reference | Road Name | Location | Treatment Area (if applicable) |  | Description of works | Aniticipated Programme Delivery Date (Spring/Summer/Autumn/Winter) | Status Update ( Programmed/Completed)
|  |  |  | Start Point | Finish Point
A0444 | 12900286 | Stapenhill Road | Burton Upon Trent | A5189 St Peters Bridge Island | A0511 Junction | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0511 | 12900922 | Bridge Street | Tutbury | Tutbury Bypass | County Boundary | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0511 | 12900802 | Tutbury Bypass | Tutbury | Bridge Street | Burton Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0511 | 12900485 | Tutbury Road | Burton Upon Trent | Beamhill Road | Calais Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0511 | 12900771 | Tutbury Road Rural | Burton Upon Trent | Burton Road | Beamhill Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A5121 | 12900454 | Byrkley Street | Burton upon Trent | Waterloo Street | Derby Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A5121 | 12901641 | Parkway | Burton upon Trent | A38 junction | U4038 Parkway | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A5121 | 12900325 | Waterloo Street | Burton upon Trent | Wellington Street | Byrkley Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A5121 | 12900331 | Wellington Road | Burton upon Trent | U4038 Parkway | B5017 Shobnall Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A5121 | 12900442 | Wellington Street | Burton upon Trent | B5017 Shobnall Road | Byrkley Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0518 | 12901085 | Stafford Road | Uttoxeter | Old Knotty Way roundabout | Approx 200m east of Loxley Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A5189 | 12900419 | Evershed Way | Burton upon Trent | C0357 Anglesey Road Island | B5018 Orchard St Island | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A5189 | 12900233 | Orchard Street | Burton upon Trent | B5018 Orchard St Island | B5018 Branston Road Island | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A5189 | 12900361 | Shobnall Road | Burton upon Trent | A5121 Wellington St Island | C0357 Anglesey Road Island | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0522 | 37700823 / 12900571 | Uttoxeter Road | Beamhurst | JCB factory roundabout | C0251 Mill Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B5008 | 12900227 | Newton Road | Burton upon Trent | A0511 Junction | County Boundary | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B5017 | 12900389, 12900120 | Henhurst Hill | Burton upon Trent | Postern Road | Recycling joint adjacent Oakley Grange | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B5017 | 12900435 | New Street | Burton upon Trent | High Street RAB | B5018 Orchard Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B5018 | 12900393 | Guild Street | Burton upon Trent | Horninglow Street | Station Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B5018 | 12900319 | Union Street | Burton upon Trent | Station Street | New Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B5018 | 12900233 | Orchard Street | Burton upon Trent | New Street | Evershed Way | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B5018 | 12900455 | Branston Road | Burton upon Trent | A5189 Orchard Street | C0357 Anglesey Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B5018 | 12900065 | Burton Road | Burton upon Trent | C0357 Anglesey Road | U4017 Warren Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B5018 | 12900004 | Main Street | Burton upon Trent | U4017 Warren Lane | A5121 Wellington Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B5027 | 12901007 | Bramshall Road | Uttoxeter | Byrds Lane | B5027 Stone Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B5027 | 12901210 / 12901111 | Oldfields Road/Stone Road | Uttoxeter | Carter Street / Hockley Road | Smithfield Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B5416 | 12900523 | Station Street | Burton upon Trent | Guild Street | Start of block paving at Worthington Way | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0018 | 12900922 | Bridge Street | Tutbury | Tutbury Bypass RAB | Lower High Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0018 | 12900761 | High Street | Tutbury | Cornmill Lane | Duke Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0018 | 12901761 | Lower High Street | Tutbury | Monk Street | Cornmill Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0058 | 12900480 | Beamhill Road | Anslow | Outwoods Lane | A0511 Tutbury Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0058 | 12900413 | Bitham Lane | Stretton | Rollesston Road | Craythorne Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0058 | 12900444 | Harehedge Lane | Outwoods | A0511 Tutbury Road | Rolleston Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0058 | 12901598 | Hopley Road | Anslow | Henhurst Hill | Outwoods Lane (C-D-S) | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0058 | 12900677 | Main Road | Anslow | Outwoods Lane (C-D-S) | Outwoods Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0058 | 12901599 | Postern Road | Tatenhill | Henhurst Hill | Callingwood Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0058 | 12900847 | Main Street | Tatenhill | Callingwood Lane | Branston Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0091 | 12900905 | Castle Street | Tutbury | Park Lane | Monk Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0091 | 12900880 | Duke Street | Tutbury | Monk Street | High Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0091 | 12900885 | Coton Lane | Draycott In The Clay | A515 Station Road | Property-Salt Meadow Farm | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
C0091 | 12900864 | Fauld Lane | Coton In The Clay | Property-Salt Meadow Farm | Property-Faulds Hall | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
C0091 | 12900886 | Fauld Lane | Fauld | Property-Faulds Hall | Property-Near Woodhouse Farm | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
C0091 | 12900755 | Fauld Lane | Tutbury | Property-Near Woodhouse Farm | Owens Bank | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
C0091 | 12900715 | Owens Bank | Tutbury | Fauld Lane | Park Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
C0091 | 12900815 | Park Lane | Tutbury | Redhill Lane | The Close | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0091 | 12900702 | Station Road | Rolleston On Dove | Burnside | School Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0359 | 12900182 | Main Street | Burton upon Trent | A444 St. Peters Street RAB | Hill Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0359 | 12900524 | Rosliston Road | Burton upon Trent | Hill Street | County boundary nr Walton Rd | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2530 | 12901013 / 12901045 | Carter Street/Hockley Road | Uttoxeter | High Street | Oldfields Road/Stone Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2530 | 12902088 | Drovers Close | Uttoxeter | Carter Street | ends | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2530 | 12901141 | Balance Street | Uttoxeter | Pinfold Street | Market Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2530 | 12901120 | Market Street | Uttoxeter | Balance Street | ends | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2530 | 12901181 | Market Place | Uttoxeter | Carter Street | Bridge Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2530 | 12901098 | Trinity Road | Uttoxeter | Bridge Street | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2530 | 12901075 | Pinfold Street | Uttoxeter | Balance Street | Railway crossing | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2531 | 12901111 | Stone Road | Uttoxeter | Carter Street | B5027 Stone Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2532 | 12901073 | Picknalls Avenue | Uttoxeter | Oldfields Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3441 | 12900722 | Castle Hayes Lane | Tutbury | Redhill Lane | Gated Entrance prior to farm | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3442 | 12900715 | Redhill Lane | Tutbury | Park Lane | Belmont Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3443 | 12900904 | Castle Hill | Tutbury | Castle Street | Property : Castle Gates | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3443 | 12900910 | Chapel Street | Tutbury | Church Street | Monk Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3443 | 12900776 | Church Street | Tutbury | Castle Street | Monk Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3443 | 12901863 | The Close | Tutbury | Psrk Lane | Park Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3444 | 12900774 | Chatsworth Drive | Tutbury | Ironwalls Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3444 | 12900763 | Ironwalls Lane | Tutbury | Ludgate Street | Burton Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3445 | 12900872 | Green Lane | Tutbury | Ironwalls Lane | Belmont Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3451 | 12900896, 12900087 | Craythorne Road | Rolleston On Dove | Beacon Road | Bitham Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3452 | 12900924 | Anslow Lane (Rolleston) | Rolleston On Dove | Burnside | A0511 Tutbury Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3461 | 12900685 | Hanbury Road | Anslow | C0018 Tutbury Road | Hopley Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3462 | 12900767 | Anslow Road | Hanbury | C0018 Tutbury Road | Near Villa Cottage (SD Joint) | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3509 | 12901502 | Bourne Close | Tutbury | Holts Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3509 | 12900865 | Ferrers Avenue | Tutbury | Norman Road | Redhill Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3509 | 12900865 | Ferrers Avenue | Tutbury | Ferrers Avenue | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3509 | 12900756 | Fishpond Lane | Tutbury | Duke Street | Wakefield Avenue | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3509 | 12900855 | Hillcrest | Tutbury | Ferrers Avenue | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3509 | 12901426 | Hillside | Tutbury | Castle Street | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3509 | 12900762 | Holts Lane | Tutbury | Silk Mill Lane | Redhill Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3509 | 12900762 | Holts Lane | Tutbury | Holts Lane | Ferrers Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3509 | 12900861 | Lancaster Drive | Tutbury | Ferrers Avenue | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3509 | 12900835 | Norman Road | Tutbury | Ludgate Street | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3509 | 12900820 | Priory Close | Tutbury | Ferrers Avenue | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3509 | 12900821 | Queens Rise | Tutbury | Ferrers Avenue | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3509 | 12901527 | Rushton Close | Tutbury | Holts Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3509 | 12900691 | Silk Mill Lane | Tutbury | Duke Street | Holts Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3509 | 12900733 | The Park Pale | Tutbury | Norman Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3509 | 12900783 | Wakefield Avenue | Tutbury | Fishpond Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3511 | 12900726 | Fairfield Avenue | Rolleston On Dove | Walford Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3511 | 12900737 | Walford Road | Rolleston On Dove | Dovecliffe Road | South Hill (Private Road) | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3514 | 12900666 | Hall Road (Inc. CDS's) | Rolleston On Dove | Church Road | The Lawns | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3514 | 12900665 | The Lawns | Rolleston On Dove | Hall Road | Burnside | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3515 | 12900897 | Croft Close | Rolleston On Dove | Station Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3517 | 12900853 | Hawksley Drive | Rolleston On Dove | Burnside | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3518 | 12900692 | Babbington Close | Tutbury | Portway Drive | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3518 | 12900693 | Cromwell Close | Tutbury | Portway Drive | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3518 | 12900818 | Pinfold Close | Tutbury | Belmont Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3518 | 12900819 | Portway Drive | Tutbury | Belmont Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3521 | 12901856 | Shotwood Close | Rolleston On Dove | Church Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3522 | 12901800 | Ealand Street | Rolleston On Dove | Forest School Street | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3522 | 12901801 | Forest School Street | Rolleston On Dove | Garrett Square | Sherholt Road (Private Road) | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3522 | 12901799 | Garrett Square | Rolleston On Dove | Forest School Street | Ealand Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3522 | 12901798 | Needwood Avenue | Rolleston On Dove | Station Road | Garrett Square | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3522 | 12900735 | Twentylands | Rolleston On Dove | Station Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3533 | 12900740 | Alderbrook Close | Rolleston On Dove | Station Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3557 | 12900850 | Meadow View | Rolleston On Dove | Station Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U4001 | 12900380 | Lichfield Street | Burton upon Trent | A5189 Orchard Street | High Street RAB | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U4001 | 12900167 | High Street | Burton upon Trent | Worthington Way | Bridge Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U4008 | 12900460 | Kitling Greaves Lane | Beamhill | A0511 Tutbury Road | Property : No.98 | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U4022 | 12900197 | Longhedge Lane | Anslow | Beamhill Road | A0511 Tutbury Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U4022 | 12900520 | Beam Close | Beamhill | Beamhill Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0051 | 23401215, 23401216 | Stafford Road | Longdon | Property : Church Cottage Ent | Overbridge to Orchard Farm | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0454 | 23401800 | Aldridge Road | Aldridge | Little Aston Road | Aldridge Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0454 | 23400249 | Aldridge Road | Little Aston | Aldridge Road | Walsall Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0454 | 23401801 | Little Aston Road | Aldridge | A452 Chester Road | Aldridge Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0454 | 23400250 | Walsall Road | Little Aston | Aldridge Road | County Boundary | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A4026 | 23400331 | Blake Street | Little Aston | Little Aston Lane | County Boundary | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A4026 | 23400870 | Little Aston Lane | Little Aston | Walsall Road | Blake Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A5195 | 23401343 | Burntwood Way | Burntwood | Milestone Way RAB | Footbridge near M6 Toll RBT | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A5195 |  | Burntwood Way | Burntwood | M6 Toll RBT | Ogley Hay Road RAB | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B4138 | 2709161, 23400421 | Rosemary Hill Road | Little Aston | C0011 Hardwick Road RAB | Blake Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B4138 | 23400628 | Thornhill Road | Streetly | County Boundary(Foley Rd East) | C0011 Hardwick Road RAB | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0146 | 23401652, 23401016 | Cannock Road | Burntwood | Milestone Way | Miners Way | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0176 | 23400818 | Mill Lane | Mill Green | A452 Chester Road | A0454 Aldridge Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0306 | 23400317 | Claypit Lane | Lichfield | D3103 Fosseway Lane | Wall Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0352 | 23400941 | Beacon Street | Lichfield | Pinfold Road | The Close | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0352 | 23401838 | Bird Street | Lichfield | The Close | Minster Pool Walk | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0352 | 23400662 | Stafford Road | Lichfield | A5192 Eastern Avenue | Pinfold Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0352 | 23400649 | Swan Road | Lichfield | Minster Pool Walk | The Friary | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3141 | 23400212 | Cross in Hand Lane | Lichfield | Pinfold Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D3358 | 23400303 | Long Bridge Road | Lichfield | Cricket Lane | London Road (Serv Rd) | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3358 | 23400069 | Cromwells Meadow | Lichfield | Long Bridge Road | London Road (Serv Rd) | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3358 | 23401435 | London Road (Serv Rd) | Lichfield | A5206 London Road | A5206 London Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3371 | 23401080 | Elgar Close | Lichfield | Purcell Avenue | Oakley Close (Private) | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3371 | 23400412 | Ponesfield Road | Lichfield | Curborough Road | Purcell Avenue | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3371 | 23400749 | Ponesgreen | Lichfield | Ponesfield Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3371 | 23400668 | Stowecroft | Lichfield | Netherstowe | Netherstowe | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3371 | 23400669 | Stychbrook Gardens | Lichfield | Ponesfield Road | Curborough Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3371 | 23400073 | Walkers Croft | Lichfield | Netherstowe | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3372 | 23400929 | Auchinleck Drive | Lichfield | Netherstowe | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3372 | 23401113 | Fecknam Way | Lichfield | Netherstowe | Brownsfield Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3372 | 23400355 | Gilbert Road | Lichfield | Verdi Court | Eastern Avenue + C-D-S | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3372 | 23401179 | Hayworth Road | Lichfield | Fecknam Way | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3372 | 23400465 | Johnson Close | Lichfield | Fecknam Way | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3372 | 23400670 | Sullivan Way | Lichfield | Gilbert Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3372 | 23400620 | Verdi Court | Lichfield | Netherstowe | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3375 | 23400942 | Beaconfield | Lichfield | Beacon Street | Swinfen Broun Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3375 | 23400526 | Erasmus Way | Lichfield | Swinfen Broun Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3375 | 23401162 | Greenhough Road | Lichfield | Beacon Street | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3375 | 23401264 | Jordan Close | Lichfield | Swinfen Broun Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3375 | 23400865 | Lillington Close | Lichfield | Beaconfield | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3375 | 23400720 | Seckham Road | Lichfield | Swinfen Broun Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3375 | 23400075 | Shaw Lane | Lichfield | Beacon Street | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3375 | 23400650 | Swinfen Broun Road | Lichfield | Erasmus Way | Jordan Close | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3376 | 23400159 | Abnalls Croft | Lichfield | Abnalls Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D3376 | 23400912 | Abnalls Lane | Lichfield | Beacon Street | A0051 Western Bypass | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D3376 | 23401177 | Hayes View | Lichfield | Lynfield Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D3376 | 23400077 | Lynfield Road | Lichfield | Abnalls Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D3376 | 23401576 | Patrick Mews | Lichfield | Abnalls Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3376 | 23400771 | Pinfold Road | Lichfield | Lynfield Road | Beacon Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D3377 | 23400940 | Beacon Gardens | Lichfield | Beacon Street | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3377 | 23400053 | Forge Lane | Lichfield | Beacon Street | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3377 | 23400809 | Nether Beacon | Lichfield | Beacon Street | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3377 | 23400688 | Smithy Lane | Lichfield | Forge Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3378 | 23400909 | Kean Close | Lichfield | Beacon Street | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3378 | 23400837 | Lyn Avenue | Lichfield | Beacon Street | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3381 | 23400937 | Barn Close | Lichfield | Meadowbrook Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3381 | 23400528 | Fallow Field | Lichfield | Meadowbrook Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3381 | 23400548 | Field Road | Lichfield | Meadowbrook Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3381 | 23401147 | Harwood Road | Lichfield | Curborough Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3381 | 23400464 | Jackson Road | Lichfield | Harwood Road | Simpson Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3381 | 23400307 | Meadowbrook Road | Lichfield | Harwood Road | Purcell Avenue | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3381 | 23401351 | Ploughmans Walk | Lichfield | Shepherd Close | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3381 | 23401352 | Shepherd Close | Lichfield | Meadowbrook Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3381 | 23400707 | Simpson Road | Lichfield | Harwood Road | Meadowbrook Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3402 | 23400046 | Gloucester Close | Lichfield | Worcester Close | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3402 | 23400452 | Lincoln Close | Lichfield | Eastern Avenue | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3402 | 23400794 | Norwich Close | Lichfield | Eastern Avenue | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3402 | 23400736 | Salisbury Close | Lichfield | Lincoln Close | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3402 | 23400690 | Southwark Close | Lichfield | Norwich Close | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3402 | 23400047 | Truro Close | Lichfield | Worcester Close | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3402 | 23400577 | Winchester Close | Lichfield | Lincoln Close | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3402 | 23400567 | Worcester Close | Lichfield | Eastern Avenue | Truro Close | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0051 | 39400323 | Anker Drive | Tamworth | Bolebridge Street RAB | Glascote Rd RAB | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0051 | 39400222 | Bolebridge Street | Tamworth | Bolebridge Street RAB | Glascote Rd RAB | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0051 | 39400007 | Lichfield Road | Tamworth | Coton Lane Island | Tame Drive Island | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0051 | 39400148 | Tamworth Road | Tamworth | Peelers Way roundabout | B5404 Watling Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B5493 | 39400008 | Lichfield Street | Tamworth | Tame Drive Island | Aldergate Junction (Inc. Ped xing) | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0036 | 23401643 | Watling Street | Weeford | A5 Weeford RAB | Flats Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0036 | 23401418 | Watling Street | Hints | Flats Lane | B5404 Watling St / A5 Slip Rd | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0152 | 23401070 | Drayton Lane | Drayton Bassett | A0453 Carroway Head | A4091 Coleshill Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0189 | 23401093 | Flats Lane | Whittington Heath | C0036 Watling Street | Knox Grave Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0189 | 23401743 | Jerrys Lane | Whittington Heath | Knox Grave Lane | A0051 Tamworth Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3013 | 23400339, 23401059, 23400120 | Darnford Lane | Whittington | Ryknild Street | Church Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3036 | 23400128 | Salts Lane | Drayton Bassett | A4091 Coleshill Road | Drayton Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3248 | 23400325 | Church Close | Drayton Bassett | Drayton Lane | End of cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3316 | 23400739 | Rectory Lane | Drayton Bassett | Drayton Lane | End of cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3332 | 23400821 | Moat Drive | Drayton Bassett | Drayton Lane | End of cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3332 | 23400289 | Old Manor Close | Drayton Bassett | Moat Drive | End of cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D3332 | 23400176 | Peel Close | Drayton Bassett | Drayton Lane | End of cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0034 | 27001142 | London Road | Newcastle | Stoke City boundary, approx 80m South East of Hospital junction | Grosvenor Island/Brook Lane roundabout | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0050 | 27001116 / 27001325 | Liverpool Road | Kidsgrove | Approx 100m North West Gloucester Road | Mount Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0051 | 27001982 | Nantwich Road | Willoughbridge | Junction A53 Newcastle Road (Blackbrook) | County boundary | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0053 | 27001531 | Newcastle Road | Red Bull | County boundary | Wickey Tree Farm access | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B5044 | 27000192 | Pepper Street | Silverdale | A525 Keele Road | High Street RAB | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0255 | 27001588 | Napley Road | Napley | B5415 | county boundary, approx 1465m northwest of B5415 | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0266 | 27001501 | Stoneyford | Peatswood | C0221 Tag Lane | County boundary, approx 25m southwest of canal bridge | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0363 | 27000527 / 27000323 / 27000884 | Coalpit Hill/Swan Bank/Crown Bank | Talke | A5011 Linley Road junction | Jamage Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2034 | 27001064 | Jamage Road/Pit Lane | Talke Pits | High Street | Approx 40m West of High Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2034 | 27001063 | Jamage Road | Talke Pits | Pit Lane | Oaktree Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2035 | 27000558 | Woodstock Road | Kidsgrove | Nelson Bank | Stoke City boundary, approx 325m northeast of Nelson Bank | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2035 | 27000143 / 27000079 / 27000080 | Boathorse Rd/Nelson Bank/Acres Nook | Kidsgrove | B5371 The Avenue | Ravenscliffe/abbitior/Travellers camp entrance | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2039 | 27001611 | Whitfield Road | Kidsgrove | Mount Road | Nabbs Close | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2039 | 27001631 | Burnwood Grove | Kidsgrove | Whitfield Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2039 | 27001670 | Mossfield Crescent | Kidsgrove | Whitfield Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2039 | 27001869 | Diamond Avenue | Kidsgrove | Whitfield Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2039 | 27001821 | Ash View | Kidsgrove | Whitfield Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2039 | 27001828 | Nabbs Close | Kidsgrove | Whitfield Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2039 | 27001199 | Parklands | Kidsgrove | Mount Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2039 | 27001098 | Larkfield | Kidsgrove | Parklands | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2039 | 27001087 | Kingswood | Kidsgrove | Parklands | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2039 | 27000318 | Summerfield | Kidsgrove | Kingswood | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2039 | 27000082 | Charnwood | Kidsgrove | Parklands | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2039 | 27000273 | Silverwood | Kidsgrove | Parklands | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2039 | 27000782 | Briarswood | Kidsgrove | Parklands | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2058 | 27001001 | Haddon Grove | Chesterton | B5369 Wolstanton Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
U2058 | 27000490 | Farcroft Avenue | Chesterton | B5369 Wolstanton Road | Willard Close | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2058 | 27002091 | Croftstead Close | Chesterton | Farcroft Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2058 | 27002090 | Willard Close (Inc cul de sacs) | Chesterton | Farcroft Avenue | ends | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2058 | 27001019 | Heath Street | Chesterton | B5369 Wolstanton Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2059 | 27001168 | Romney Avenue | Chesterton | Loomer Road | Gainsborough Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
U2059 | 27000489 | Gainsborough Road | Chesterton | Castle Street | Romney Avenue | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
U2059 | 27001244 | Reynolds Avenue | Chesterton | Romney Avenue | Gainsborough Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
U2059 | 27000697 | Albert Street | Chesterton | B5500 London Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
U2059 | 27000565 | Sutton Street | Chesterton | B5500 London Road | Castle Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
U2059 | 27000874 | Cooper Street | Chesterton | Castle Street | Emberton Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
U2059 | 27000492 | Emberton Street | Chesterton | Cooper Street | Mount Pleasant | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
U2059 | 27000137 | Mount Pleasant | Chesterton | Emberton Street | Gainsborough Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
U2059 | 27001044 | Hogarth Place | Chesterton | Romney Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
U2059 | 27000051 | Constable Avenue | Chesterton | Romney Avenue | Loomer Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
U2059 | 27000695 | Landseer Place | Chesterton | Constable Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
U2059 | 27000697 | Park Court (Albert Street) | Chesterton | Albert Street | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2059 | 27001267 | Warwick Street | Chesterton | B5500 London Road | Castle Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2059 | 27001979 | Queen Street | Chesterton | Victoria Street | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2059 | 27001980 | King Street | Chesterton | Victoria Street | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2065 | 27000128 | Stonewall Place | Silverdale | B5044 Newcastle Street | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2067 | 27000501 | Daleview Drive (Inc cul de sacs) | Silverdale | Park Road | ends | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2067 | 27000966 | Glenwood Close | Silverdale | Daleview Drive | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2067 | 27000398 | Vale Street | Silverdale | Chapel Street | Church Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2067 | 27000206 | Redheath Close | Silverdale | B5044 Pepper Street | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2076 | 27001765 | Lyme Valley Road | Newcastle | Brook Lane | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2079 | 27001302 | Grosvenor Road | Newcastle | A34 London Road | Belgrave Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2079 | 27000654 | Grosvenor Gardens | Newcastle | Grosvenor Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2079 | 27000755 | Belgrave Road | Newcastle | Grosvenor Road | Vessey Terrace | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2079 | 27001301 | Vessey Terrace | Newcastle | A34 London Road | Victoria Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2079 | 27000404 | Well Street | Newcastle | Bankside | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2079 | 27000979 | Garden Street | Newcastle | Bankside | Hassell Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2080 | 27000123 | Miller Street | Newcastle | A53 King Street | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2080 | 27000396 | Water Street | Newcastle | A52 George Street | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2080 | 27000260 | Seagrave Street | Newcastle | A52 George Street | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2080 | 27000441 | Wharf Street | Newcastle | A52 George Street | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2080 | 27001047 | John Street | Newcastle | A52 George Street | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2080 | 27001192 | Poplar Grove | Newcastle | Albert Street | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2080 | 27000516 | Earl Street | Newcastle | Albert Street | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2082 | 27000687 | Bailey Street | Newcastle | B5367 Knutton Lane | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2082 | 27000918 | Dunkirk (Inc cul de sac leading to Montgomery Court) | Newcastle | B5367 Knutton Lane | Castle Hill Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2082 | 27000588 | Poolside | Newcastle | Dunkirk | Stanier Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2082 | 27000975 | Greenside | Newcastle | Dunkirk | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2082 | 27000947 | Fletcher Bank | Newcastle | Dunkirk | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2082 | 27000824 | Castle Hill Road | Newcastle | Dunkirk | Stanier Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2082 | 27000824 | Castle Hill Road | Newcastle | Castle Hill Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2082 | 27001046 | John O Gaunts Road | Newcastle | Stanier Street | B5044 Silverdale Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2083 | 27000734 | Ashfields New Road | Newcastle | A34 Liverpool Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2083 | 27000648 | Hill Street | Newcastle | Ashfields New Road | Jason Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2083 | 27001206 | Mellard Street | Newcastle | Hill Street | Jason Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2083 | 27000468 | Jason Street | Newcastle | Hill Street | Ashfields New Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2083 | 27000214 | Prospect Terrace | Newcastle | B5367 Knutton Lane | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2084 | 27000084 | Mayer Avenue | Newcastle | A34 Liverpool Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2084 | 27000989 | Goodwin Avenue | Newcastle | A34 Liverpool Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2084 | 27001057 | Kimberley Road | Newcastle | A34 Liverpool Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2084 | 27000695 | Albany Road | Newcastle | A34 Liverpool Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2084 | 27000721 | Baden Street | Newcastle | Albany Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2085 | 27000779 | The Hollies | Newcastle | A527 Brampton Road | Limit of adoption approx 135m West A527 Brampton Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2086 | 27000596 | Sidmouth Avenue | Newcastle | A527 Brampton Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2086 | 27000155 | Northcote Place | Newcastle | A53 King Street | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U2112 | 27001827 | Ironbridge Drive | Newcastle | B5044 Silverdale Road | ends | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0520 | 37700678 / 37700530 | Leek Road | Moorville | Roughcote Lane | 30mph limit Cellarhead | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0520 | 37701923 | Cheddleton Road | Birchall | Sheephouse Farm access | Brittania Society roundabout | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0520 | 37700987 | Leek Road | Cellarhead | 50/30mph Cellarhead | 30/50mph Wetley Rocks | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0520 | 37702170 | Cheadle Road | Wetley Rocks | 30/50mph limit near Ashcombe Park entrance | A522 Consall Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0522 | 37702170 | Cheadle Road | Consall | A520 Main Road | A52 Blakeley Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0523 | 37701961 | Ashbourne Road | Bradnop | layby near Porters Lane | B5053 Bottom House cross roads | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B5054 | 37700579 | New Road | Warslow | B5053 Longnor Road | Approx 1100m east 30mph near Cowlow Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B5054 | 37700579 | Warslow Road | Butterton | C0095 Parsons Lane | Approx 280m south west Dog Lane (top of bank) | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B5417 | 37700619 | Oakamoor Road | Highshutt | Approx 250m east Lockwood Road | Greendale | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
BOAT | 37701657 | Birchall Lane | Leek | A520 Cheddleton Road | end (limit of HMPE approx 275m north east) | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0017 | 37700074 | Thorncliffe Lane | Thorncliffe | A53 Buxton Road | C0016 Thorncliffe Bank | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0082 | 37701271 | Grange Road | Biddulph | A527 Congleton Road | 60/30mph speed limit by Hurst Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0158 | 37701597 | Apesford Lane | Bradnop | C0064 Basford Green Road | A523 Ashbourne Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0238 | 37700212 | Breach Lane | Totmonslow | C0109 Draycott Road | A522 Cheadle Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0355 | 37701173 / 37700608 | Park Lane/New Street | Biddulph Moor | Mill Hayes Road | C0355 Rudyard Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0355 | 37701395 | Rudyard Road | Biddulph Moor | C0355 New Street | C0173 Top Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1078 | 37700868 | Woodhouse Lane | Biddulph Moor | Over The Hill | New Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1082 | 37701406 / 37701312 | Hurst Road/Over The Hill | Biddulph Moor | C0082 Grange Road | Woodhouse Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1082 | 37700896 | Under The Hill | Biddulph Moor | Hurst Road | Woodhouse Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1198 | 37700526 | Leek Lane | Biddulph Moor | New Street | Lask Edge Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1199 | 37701457 | Elliases Lane | Biddulph Moor | Hurst Road | Dam Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1199 | 37700342 | Dam Lane | Biddulph Moor | Elliases Lane | Over The Hill | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1199 | 37701309 | School Lane | Biddulph Moor | Hot Lane | Dam Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1199 | 37700292 | Church Lane | Biddulph Moor | School Lane | Woodhouse Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1199 | 37700487 | Hot Lane | Biddulph Moor | Rudyard Road | Top Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1280 | 37700546 | Lotus Avenue (inc cul de sac) | Biddulph | Lyneside Road | Endon Drive | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1280 | 37700819 | Turnlea Close | Biddulph | Lotus Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1280 | 37700506 | Kestrel Close | Biddulph | Lotus Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1280 | 37701335 | Knype Way | Biddulph | Lotus Avenue | Farnworth Close | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1280 | 37700390 | Farnworth Close | Biddulph | Knype Way | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1280 | 37700809 | Tower Close | Biddulph | Mansfield Drive | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1280 | 37701061 | Endon Drive (inc cul de sac) | Biddulph | Mansfield Drive | ends | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1280 | 37701453 | Mansfield Drive | Biddulph | Endon Drive | Tower Hill Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1280 | 37700739 | Stile Close | Biddulph | Tower Hill Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1280 | 37700614 | Newpool Terrace | Brown Lees | Tower Hill Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1280 | 37701333 | Cowlishaw Close | Brown Lees | Brown Lees Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1280 | 37700410 | Gardeners Close | Brown Lees | Brown Lees Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1280 | 37700573 | Lyndhurst Drive | Biddulph | Tower Hill Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1280 | 37700498 | James Way | Biddulph | Newpool Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1280 | 37701187 | Lynesdie Road (Inc spur) | Biddulph | Newpool Road | Brown Lees Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1280 | 37700520 | Lanchester Close | Biddulph | Lyneside Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1280 | 37701334 | Lagonda Close | Biddulph | Lyneside Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1280 | 37700521 | Lancia Close | Biddulph | Lyneside Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1280 | 37700436 | Hambleton Place | Biddulph | Lyneside Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1280 | 37701030 | Gilbern Drive | Biddulph | Lyneside Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1280 | 37701180 | Healey Avenue | Biddulph | Lyneside Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1280 | 37700611 | Minerva Close | Biddulph | Lyneside Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1280 | 37700939 | Royce Avenue | Biddulph | Lyneside Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1280 | 37700209 | Bateman Avenue | Biddulph | Lyneside Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1280 | 37701768 | Farnham Drive | Biddulph | Lyneside Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1282 | 37700384 | Essex Drive | Biddulph | Mow Lane | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1282 | 37701250 | York Close | Biddulph | Essex Drive | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1289 | 37700200 | Birchall Park Avenue | Leek | A520 Cheddleton Road | end (limit of adoption approx 100m north east) | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1289 | 37700689 | Sandybrook Lane | Leek | A520 Cheddleton Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1289 | 37701656 | Woodland Close | Leek | Sandybrook Lane | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1289 | 37701254 | Rivendell Lane | Leek | Sandybrook Lane | Birchall Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1289 | 37700185 | Ashenhurst Way | Leek | A520 Cheddleton Road | Approx 185m west of A520 Cheddleton Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1289 | 37700518 | Ladydale Close | Leek | Ashenhurst Way | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1289 | 37701243 | Ashcombe Way | Leek | Ashenhurst Way | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1289 | 37700154 | Ballington View | Leek | A520 Cheddleton Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1289 | 37701228 | Cauldon Close | Leek | Ashcombe Way | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1292 | 37701686 / 37700802 | Ball Haye Rd/Vicarage Rd/Ball Haye Gr/Haregate Rd/Windsor Dr | Leek | A523 Buxton Road | Novi Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1292 | 37700652 / 37701145 | Portland Street North/Rose Bank Street | Leek | A523 Buxton Road | Ball Haye Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1292 | 37701686 | Ball Haye Rd (side road) | Leek | Vicarage Road | Vicarage Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1292 | 37700401 | Fowlchurch Road | Leek | Ball Haye Road | Limit of adoption approx 265m north | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1292 | 37700991 | Lancaster Avenue | Leek | Ball Haye Road | ends | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1292 | 37700962 | Nelson Street | Leek | Ball Haye Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1292 | 37700971 | Milk Street | Leek | Ball Haye Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1292 | 37700948 | Prince Street | Leek | Ball Haye Green | A523 Buxton Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1292 | 37701816 | Hayes Close | Leek | Prince Street | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1292 | 37701762 | Pump Street | Leek | Ball Haye Green | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1292 | 37700958 | Novi Lane | Leek | Ball Haye Green | A53 Buxton Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1292 | 37700684 | Provost Place | Leek | Novi Lane | Hall Avenue | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1292 | 37700610 | Milner Terrace | Leek | Novi Lane | Carlton Terrace | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1292 | 37701139 | Hall Avenue (both parts) | Leek | Milner Terrace | ends | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1292 | 37701766 | Haig Road | Leek | Milner Terrace | Carlton Terrace | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1292 | 37701480 | Carlton Terrace | Leek | Prince Street | Abbotts Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1292 | 37701481 | Beatty Road | Leek | Carlton Terrace | Carlton Terrace | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1292 | 37701483 | Weston Street | Leek | A523 Buxton Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1292 | 37700827 | Victoria Street | Leek | Weston Street | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1292 | 37701482 | Shaw Place | Leek | A523 Buxton Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1292 | 37700193 / 37701358 | Abbotts Road/Queens Drive | Leek | A53 Buxton Road | Haregate Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1292 | 37700763 | The Crescent | Leek | Abbotts Road | Abbotts Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D1292 | 37700846 | Westminster Road (Inc spur) | Leek | Haregate Road | Abbotts Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1292 | 37700176 | Argles Road | Leek | Haregate Road | Abbotts Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1292 | 37700176 | Argles Road | Leek | Westminster Road | Argles Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1292 | 37701359 | Tittesworth Avenue | Leek | Haregate Road | Haregate Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1292 | 37700485 | Horsecroft Crescent | Leek | Haregate Road | Queens Drive | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1292 | 37701812 | Horsecroft Grove | Leek | Horsecroft Crescent | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1292 | 37704171 | The Doves | Leek | Haregate Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1292 | 37701051 | Furnston Place | Leek | Westminster Road | ends | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1292 | 37700949 | Priory Avenue | Leek | Haregate Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1292 | 37700301 | Churnet View | Leek | Haregate Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1292 | 37700938 | Roche Avenue | Leek | Haregate Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1292 | 37704169 | Osprey Close | Leek | Haregate Road | ends | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1292 | 37700942 | Ramshaw View | Leek | Horsecroft Crescent | Queens Drive | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1292 | 37700656 | Princess Avenue | Leek | Queens Drive | Windsor Drive | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1292 | 37700777 | Thorncliffe View | Leek | Princess Avenue | ends | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1292 | 37700654 | Prince Charles Avenue | Leek | Princess Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D1300 | 37700199 | Birchall Close | Leek | A520 Cheddleton Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A5013 | 37601294 | Eccleshall Road | Great Bridgeford | B5405 Woodseaves Road | 30mph limit to the east of B5405 | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0513 | 37601238 | Beaconside | Stafford | West side of Marston Lane | Approx 150m north B5066 Sandon Rd Stafford side | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0513 | 37601238 | Beaconside | Stafford | Approx 485m south B5066 Sandon Rd Stafford side | A518 Weston Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A5182 | 37602824 | Whitmore Road | Hanchurch | A519 Newcastle Road | Approx 75m east Rock Hall Farm access | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A5182 | 37601358 | Weston Road | Stafford | A513 Beaconside | Riverway | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A5187 | 37600478 | Tenterbanks | Stafford | Broadeye | Victoria Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0519 | 37600931 | Newcastle Road | Cotes Heath | S/D joint near Nelson Crescent | Approx 400m south A51 Stone Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0519 | 37602051 | Newport Road | Forton | County Boundary | Approx 250m North of Shay Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B5027 | 37601510 | Newcastle Road | Stone | A34 The Fillybrooks | Approx 25m West of Canal Bridge | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B5027 | 37602128 | Lichfield Road | Stone | A520 Christchurch Way | A51 Lichfield Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B5066 | 37600625 | Gaol Road | Stafford | Gaol Square | Sandon Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B5066 | 37600423 | Sandon Road | Stafford | Gaol Road | Astonfields Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B5405 | 37600855 | Woodseaves Road | Great Bridgeford | A5013 Eccleshall Road | Lane by Ladfordfields Industrial estate | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0001 | 37600913 | Tittensor Road | Swynnerton | A51 Stone Road | C0314 Cotes Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0037 | 37601985 | Lea Road | Adamston | D2372 Lea Road (Lea Heath) | Property The Wicket PH | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0037 | 12900930, 12900931 | Lea Road | Newton | Property The Wicket PH | B5013 Uttoxeter Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0178 | 37601525 / 37604692 | Garshall Green Lane/The Allways | Garshall Green | B5027 Stone Road | C185 Sharpley Heath Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0180 | 37600828 | Whetalow Brooks Road | Garshall Green | C178 Garshall Green Lane | D2167 Milwich Heath Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0219 | 37601027 / 37601673 | Drayton Road/Dog Lane | Hanchurch | A51 Stableford | A519 Newcastle Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0228 | 37601359 | Wharf Road | Gnosall | Quarry Lane jct / SD joint | Newport Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0237 | 37600825 / 37601571 | Moddershall Oaks/Knenhall Ln | Moddershall | B5066 Hilderstone Road | C0244 Knenhall | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
C0261 | 37601491 | Plardiwick Road | Gnosall | Newport Road | Back Lane jct / SD joint | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0375 | 37600755 | Rickerscote Road | Stafford | A449 Wolverhampton Road | Silkmore Ln/Rickerscote Rd RAB | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0376 | 37600413 | Riverway | Stafford | A34 Lichfield Road | A518 Weston Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0267 | 37601349 | Worston Lane | Shallowford | A5013 Eccleshall Road | S/D joint by Izaac Walton Cottage | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2082 | 37601014 | Harley Thorn Lane | Beech | A519 Newcastle Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2083 | 37601015 | Peacock Lane | Hanchurch | Hanchurch Lane | A5182 Whitmore Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2083 | 37602514 | Ridding Bank | Hanchurch | Hanchurch Lane | limit of adoption approx 240m South East | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2088 | 37601016 | Hanchurch Lane | Hanchurch | A519 Newcastle Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2149 | 37602152 | Top Lane | Beech | A519 Newcastle Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2149 | 37601764 | Beechdale Lane (Spur) | Beech | Top Lane | Beechdale Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2150 | 37601765 | Beech Cliffe Lane | Beech | A519 Newcastle Road | Winghouse Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2158 | 37600826 | Garshall Green Lane (Spur) | Garshall Green | C178 Garshall Green Lane | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2276 | 37601780 | Back Lane | Gnosall | Plardwick Road | Newport Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2276 | 37601054 | Cross Street | Gnosall | The Rank | Mill Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2276 | 37601522 | Mill Lane | Gnosall | Newport Road | Wharf Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2276 | 37602034 | The Rank | Gnosall | Newport Road | Wharf Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2276 | 37602037 | Willey Lane | Gnosall | Newport Road | Up to bridge | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2316 | 37601463 | Salt Bank | Salt | B5066 Sandon Road | Trentfield Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2338 | 37601398 | Heathway | Gnosall | Wharf Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2339 | 37601058 | Impstones | Gnosall | Wharf Road | Monks Walk | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2339 | 37601526 | Monks Walk | Gnosall | Wharf Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2339 | 37601413 | Telford Lane | Gnosall | Impstones | Monks Walk | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2339 | 37602132 | Waterside Court | Gnosall | Wharf Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2356 | 37601633 | Glendower Close | Gnosall | Newport Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2400 | 37601142 | Mill Street | Stone | Christchurch Way | Railway bridge, limit of adoption | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2400 | 37602829 | Millstone Court | Stone | Mill Street | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2404 | 37602467 | Millenium Way | Stone | Whitebridge Ln/Millenium Way RAB | Navigation Loop RAB | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2404 | 37602469 | Navigation Loop | Stone | Millenium Way RAB | Millenium Way RAB | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2404 | 37602468 | Rudyard Close | Stone | Navigation Loop | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2404 | 37602470 | Brindley Close | Stone | Navigation Loop | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2404 | 37602584 | Rangeley View | Stone | Navigation Loop | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2404 | 37602586 | Rendel Grove | Stone | Navigation Loop | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2404 | 37602587 | Bentley Close | Stone | Navigation Loop | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2404 | 37602588 | Anderton View | Stone | Navigation Loop | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2404 | 37602625 | Barnton Edge | Stone | Navigation Loop | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2404 | 37602643 | Joules Drive | Stone | Navigation Loop | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2404 | 37602745 | Cressey Close | Stone | Navigation Loop | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2404 | 37602632 | Caldon Way | Stone | Navigation Loop | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2404 | 37602665 | Harecastle Bank | Stone | Navigation Loop | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2404 | 37602666 | Saltersford Rise | Stone | Navigation Loop | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2404 | 37602585 | Rolt Close | Stone | Navigation Loop | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2404 | 37602582 | Dixon Close | Stone | Navigation Loop | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2411 | 37601231 | Priory Road (Inc spur 112 to 146) | Stone | B5027 Lichfield Road | Limit of adoption app. 55m NE Elm Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2411 | 37601410 | Sutherland Road | Stone | Priory Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2411 | 37601271 | Jervis Road | Stone | Priory Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2411 | 37601692 | De Wint Road | Stone | Priory Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2411 | 37601279 | Gower Road | Stone | Priory Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2411 | 37601231 | Priory Road (Cul de sac No.s 65 to 75) | Stone | Priory Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2411 | 37601171 | Forrester Road | Stone | Priory Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2411 | 37600970 | Willow Road (Inc spur) | Stone | Priory Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2411 | 37601685 | Crompton Road | Stone | Priory Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2411 | 37601103 | Birch Road | Stone | B5027 Lichfield Road | Priory Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2411 | 37601770 | Ash Road | Stone | Birch Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2411 | 37601047 | Oak Road | Stone | Birch Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2411 | 37601138 | Sycamore Road | Stone | Priory Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2411 | 37601296 | Elm Road | Stone | Priory Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D2433 | 37601772 | Ashdale Park | Yarnfield | Yarnfield Lane | De Havilland Drive | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2433 | 37601760 | Batten Walk | Yarnfield | Ashdale Park | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2433 | 37601314 | De Havilland Drive | Yarnfield | Ashdale Park | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2433 | 37601433 | Sopwith Close | Yarnfield | De Havilland Drive | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2433 | 37602415 | Yeager Court | Yarnfield | De Havilland Drive | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2433 | 37602167 | Henshaw Way | Yarnfield | De Havilland Drive | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2433 | 37602096 | Moorhouse Court | Yarnfield | De Havilland Drive | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2433 | 37601888 | Mitchell Rise | Yarnfield | De Havilland Drive | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2433 | 37601697 | Cobham Close | Yarnfield | Ashdale Park | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2437 | 37601710 | Church Close | Ranton | Brook Lane | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2554 | 37601741 | Brookside | Ranton | Brook Lane | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2554 | 37601361 | Whites Meadow | Ranton | Coton Lane | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2563 | 37601783 | Abbeyside | Ranton | Brook Lane | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2575 | 37600944 | The Paddocks | Yarnfield | Yarnfield Lane | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2575 | 37600939 | Calveley Close | Yarnfield | The Paddocks | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2575 | 37600940 | Potters Avenue | Yarnfield | Calveley Close | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2575 | 37600938 | College Fields | Yarnfield | The Paddocks | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2604 | 37602506 | Dyson Way | Stafford | A513 Beaconside | Whittle Rise roundabout | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D2604 | 37602506 | Dyson Way | Stafford | Whittle Rise roundabout | Whittle Rise roundabout | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4305 | 37601558 | Leese Lane | Billington | A518 Newport Road | End of cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4576 | 37601832 | Coton Back Lanes | Gnosall | Newport Road (East entrance) | Coton Back Lanes 3-way junction | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4576 | 37601832 | Coton Back Lanes | Gnosall | Newport Road (West entrance) | Coton Back Lanes 3-way junction | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4576 | 37601832 | Coton Back Lanes | Gnosall | Newport Road (South entrance) | Coton Back Lanes | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4576 | 37601832 | Coton Back Lanes | Gnosall | Coton Back Lanes 3-way junction | Beffcote Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3016 | 37600409 | Read Avenue | Stafford | Douglas Road West | Approx 20m south Prospect Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3026 | 37600299 | Hillcroft Avenue | Stafford | A513 Weeping Cross | Clevedon Avenue | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3026 | 37600639 | Clevedon Avenue | Stafford | full extents | full extents | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3026 | 37600140 | Brean Road | Stafford | Clevedon Avenue | Mendip Avenue | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3026 | 37600176 | Burnham Ave | Stafford | Brean Road | Glastonbury Close | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3026 | 37600269 | Glastonbury Close | Stafford | Burnham Avenue | ends | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3026 | 37600578 | Mendip Avenue/Overhill Road | Stafford | A34 Cannock Road | Selworthy Drive | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3026 | 37600535 | Winsford Crescent | Stafford | Mendip Avenue | Mendip Avenue | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3026 | 37600510 | Wells Drive | Stafford | Mendip Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3026 | 37600407 | Radstock Close | Stafford | Mendip Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3026 | 37600556 | Silvester Way | Stafford | Mendip Avenue | Victoria Way | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3026 | 37600311 | Island Green | Stafford | Overhill Road | Overhill Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3026 | 37600276 | Greenfield Road | Stafford | Overhill Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3026 | 37600378 | Oakridge Way | Stafford | Greenfield Road | Old Croft Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3026 | 37600569 | Oakridge Close | Stafford | Oakridge Way | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3026 | 37600666 / 37600037 | Victoria Way/Selworthy Drive | Stafford | Oakridge Way | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3026 | 37600325 | Knowle Road (Inc spur) | Stafford | A513 Weeping Cross | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3026 | 37600260 | The Firs Close | Stafford | Knowle Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3026 | 37600195 | Cremorne Drive | Stafford | Knowle Road | ends | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600391 | Parkside Avenue | Stafford | A513 Beaconside | A513 Beaconside | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600103 | Amblefield Way | Stafford | Parkside Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600121 | Aldershaw Close | Stafford | Parkside Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600712 | Darnford Close | Stafford | Parkside Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600718 | Lawnsfield Walk (Inc spur) | Stafford | Parkside Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600117 | Barlaston Close | Stafford | Parkside Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600747 | Meadow Bank Walk | Stafford | Parkside Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600643 | Chartley Close | Stafford | Parkside Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600219 | Elford Close | Stafford | Parkside Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600773 | Elmhurst Close | Stafford | Elford Close | Fairoak Avenue | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600096 | Fairoak Avenue | Stafford | Parkside Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600665 | Underwood Close | Stafford | Parkside Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600714 | Downfield Grove | Stafford | Parkside Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600097 | Springvale Rise | Stafford | Parkside Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600105 | Ashdale Drive | Stafford | Parkside Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600339 | Linksfield Grove | Stafford | Parkside Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600138 | Bradshaw Way | Stafford | Parkside Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600129 | Beton Way (Inc spur) | Stafford | Parkside Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600653 | Brackenfield Way | Stafford | Parkside Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600628 | Fellfield Way | Stafford | Parkside Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600508 | Wayfield Drive | Stafford | Parkside Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600685 | Rambleford Way | Stafford | Wayfield Drive | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600706 | Pitstone Close | Stafford | Parkside Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600107 | Ashridge Walk | Stafford | Parkside Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600231 | Felden Close | Stafford | Parkside Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600151 | Buckland Road | Stafford | Parkside Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600357 | Marsworth Way | Stafford | Buckland Road | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600751 | Aldbury Close | Stafford | Parkside Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3041 | 37600644 | Chaulden Road | Stafford | Parkside Avenue | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U3062 | 37600514 | Tilcon Avenue | Stafford | Baswich Lane | end | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0051 | 23401381, 5501424 | Leahall Way | Armitage | A0513 Armitage Road | A0051 Brereton Hill | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A4601 | 5500012 | Wolverhampton Road | Cannock | Retail Parlk entrance | Wellington Drive | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B4154 | 5500570 | Hednesford Road | Heath Hayes | Junction With Hayes Way | Junction With A5190 | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B5012 | 5501062 | New Penkridge Road | Cannock | Park Road island | Sandy Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0032 | 5500647 | Penkridge Bank Road | Cannock | Camp Road junction | Marquis Drive | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0032 | 5500059 | Penkridge Bank Road | Rugeley | Marquis Drive | Chaseley Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0032 | 5500845 | Hagley Road | Rugeley | Chaseley Road | A460 Western Springs Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U5116 | 5500667 | Canterbury Drive (Inc. of all cul-de-sacs) | Heath Hayes | Hayes Way | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U5116 | 5501514 | Chopin Close | Heath Hayes | Heath Way | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U5116 | 5500016 | Gorsemoor Road | Heath Hayes | Meadow Way | Hednesford Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U5116 | 5500836 | Hayes Way | Heath Hayes | Heath Way Island | Pheasant Way | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U5116 | 5501515 | Purcel Close | Heath Hayes | Stauss Drive | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U5116 | 5501126 | Salisbury Drive (Inc. of all cul-de-sacs) | Heath Hayes | Hayes Way | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U5116 | 5501513 | Stauss Drive | Heath Hayes | Heath Way | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
U5116 | 5501512 | Vivaldi Drive | Heath Hayes | Stauss Drive | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0034 | 36701932 | Cannock Road | Bednall | Layby South of Buxtons | Approx Nr Common Lane by property called Gatwood | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0041 | 36700199, 36700198 | Holyhead Road | Codsall | Strawmoor Lane (Up to previous S/D joint) | Wrottesley Park Road Crossroads | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0460 | 36702063, 5501474 | Lodge Lane | Cannock | A5 Watling Street RAB | C0161 Saredon Road RAB | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0460 | 36702063 | Lodge Lane | Middle Hill | C0161 Saredon Road RAB | A4601 Wolverhampton Road RAB | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
A0464 | 36700929 | Holyhead Road | Kingswood | A41 Junction | County Boundary @ D4015 County Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B4176 | 36700721 | Bridgnorth Road | Himley | Himley Lane junction | Himley Lane junction | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
B5012 | 36701430 | Cannock Road | Lower Mansty | Sandy Lane | Near Chicken Farm (Pillaton) | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0040 | 36701191 | Hollybush Lane | Oaken | Willow Lane | Oaken Lanes | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0040 | 36701619 | Shop Lane | Oaken | A0041 Holyhead Road | Willow Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0051 | 36700438 | Holly Lane | Great Wyrley | Gorsey Lane Island | A0034 Walsall Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
C0051 | 36700438 | Holly Lane | Great Wyrley | Gorsey Lane Island | Strawberry Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
C0078 | 36701469, 36700380 | Pool House Road | Wombourne | B4176 Bridgnorth Road | Clap Gate Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0078 | 36701011 | Ounsdale Road | Wombourne | Clap Gate Road | Station Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0078 | 36700186 | School Road | Wombourne | Station Road | Billy Buns Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0078 | 36700313 | Withymere Lane | Lloyds Hill | Billy Buns Road | Property - Penn Ridge | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0092 | 36700985 | Pinfold Lane | Congreve | Whiston Road | Bungham Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0342 | 36700173 | Battlefield Hill | Wombourne | Gilbert Lane | A0449 Stourbridge Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
C0342 | 36701251 | Rookery Lane | Wombourne | Greenhill | Battlefield Hill | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4015 | 36701354 | County Lane | Oaken | A0464 Holyhead Road | A0041 Newport Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4015 | 36701354 | County Lane | Kingswood | A0041 Newport Road | County Boundary | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4019 | 36700345 | Moatbrook Lane | Oaken | Wood Lane | Wood Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4020 | 36700369 | Slate Lane | Oaken | Wood Lane | Moatbrook Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4021 | 36700891 | Strawmoor Lane | Oaken | Bridge (SD Joint) | Moatbrook Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D4023 | 36700600 | Middle Lane | Oaken | A0041 Holyhead Road | Oaken Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Completed in 2024
D4025 | 36700174 | Stafford Lane | Oaken | A0041 Holyhead Road | Oaken Lanes | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4026 | 36700351 | Willow Lane | Oaken | Shop Lane | Stafford Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4027 | 36700590 | Oaken Lane | Oaken | Strawmoor Lane | Shop Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4028 | 36701200 | Hushpins Lane | Oaken | County Lane (County B'dary) | Strawmoor Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4029 | 36700625 | Barn Lane | Kingswood | A0464 Holyhead Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4118 | 36700666 | Giggerty Lane | Wombourne | Poolhouse Lane | Common Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4119 | 36701462 | Brickbridge Lane | Wombourne | Bridgnorth Road | Giggerty Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4311 | 36701261 | Haling Road | Penkridge | Bellbrook | Cannock Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4311 | 36700360 | The Saplings | Penkridge | Haling Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4311 | 36700934 | Sapling Close | Penkridge | Haling Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4311 | 36700595 | Marsh Lane | Penkridge | Teddesley Road | Haling Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4311 | 36701152 | Leacroft Road | Penkridge | Marsh Lane | Marsh Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4311 | 36700275 | Orchard Crescent | Penkridge | Leacroft Road | Leacroft Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4311 | 36700734 | Bellbrook | Penkridge | Cannock Road | Teddesley Road | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4317 | 36701070 | New Road | Penkridge | A0449 Wolverhampton Road | Market Street | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4439 | 36700110 | Hatherton Road | Penkridge | Teddesley Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4439 | 36701278 | Frederick Road | Penkridge | Teddesley Road | Littleton Crescent | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4439 | 36700622 | Kempson Road | Penkridge | Frederick Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4439 | 36701145 | Littleton Crescent | Penkridge | Kempson Road | Marsh Lane | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4439 | 36700572 | Orchard Close | Penkridge | Littleton Crescent | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4495 | 36701258 | Grosvenor Close | Penkridge | Marsh Lane | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4506 | 36700694 | Cherrybrook Drive | Penkridge | Cannock Road | Wiscombe Avenue | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4506 | 36700902 | Sprengers Close | Penkridge | Cherrybrook Drive | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4506 | 36700231 | Oakley Close | Penkridge | Cherrybrook Drive | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4506 | 36700420 | Ketmere Close | Penkridge | Cherrybrook Drive | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4506 | 36701461 | Prescott Drive | Penkridge | Cherrybrook Drive | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4506 | 36700552 | Shelsey Close | Penkridge | Cherrybrook Drive | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4506 | 36700639 | Holme Rise | Penkridge | Cherrybrook Drive | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4506 | 36700507 | Wiscombe Avenue | Penkridge | Cherrybrook Drive | Cherrybrook Drive | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4506 | 36701400 | Chelford Close | Penkridge | Wiscombe Avenue | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4506 | 36700014 | Little Marsh Grove | Penkridge | Cannock Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4560 | 36701432 | Cannock Road | Penkridge | Market Street | Wolgarston Way | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed
D4608 | 36700897 | Stanford Close | Penkridge | Cannock Road | End of the cul-de-sac | Carriageway Preventative Pre-patching Works | Between April 2024 and March 2025 | Programmed