## Sheet1
Programme Name: |  |  | Structural Maintenance Schemes
Programme Reporting Period: |  |  | April 2024 - March 2025
* All programmes of work are correct at the time of issuing. Deliverables and timeframes may be subject to change.
Road No. | Unique Street Reference | Road Name | Location | Treatment Area (if applicable) |  | Description of works | Aniticipated Programme Delivery Date (Spring/Summer/Autumn/Winter) | Status Update ( Programmed/Completed)
|  |  |  | Start Point | Finish Point
A5121 | 12900093, 12902025, | Derby Road | Burton upon Trent | James Brindley Way | Princess Way | Minor footway & kerbing along with carriageway resurfacing. | Between 4th March 2024 and 12th July 2024 | Complete
C0306 | 23401249 | Trent Valley Road | Lichfield | Junction of Wisage Road | Junction of Wisage Road | Replacement of high friction surfacing | Between 25th March 2024 and 12th April 2024 | Complete
A0034 | 37604630 | Gaol Road / Chell Road | Stafford | Island at the junction of Chell Road / Foregate Street / Gaol Road & Queensway, and Chell Road between Gaol Road island and Broadeye | Island at the junction of Chell Road / Foregate Street / Gaol Road & Queensway, and Chell Road between Gaol Road island and Broadeye | Minor kerbing along with footway and carriageway resurfacing. | Between 8th April 2024 and 6th September 2024 | Complete
A0052 | 37700178 | Ash Bank Road / Washerwall Lane junction | Werrington | Signalised junction and approaches of Ash Bank Road / Washerwall Lane & Salters Lane | Signalised junction and approaches of Ash Bank Road / Washerwall Lane & Salters Lane | Carriageway & footway resurfacing | Between 22nd January 2024 and 30th May 2024 | Complete
A0449 / A0034 | 37600566, 37602367 | Wolverhampton Road (Part) / Queensway Island | Stafford | Park Street | Queensway island | Minor kerbing along with carriageway resurfacing. | Between 4th March 2024 and 18th May 2024 | Complete
A0527 | 37701589 | Meadows Way (Inc Wharf Road Island & Tunstall Road Island) | Biddulph | Wharf Road | St.Johns Road | Minor kerbing along with carriageway resurfacing. | Between 27th May 2024 and 14th June 2024 | Complete
A0053 | 37701259 | Buxton Road | Leek | Shaw Place | Woodfield Court | Minor kerbing along with carriageway resurfacing. | Between 5th August 2024 and 5th September 2024 | Complete
A0525 | 27001014 | Higherland | Newcastle | Junction with Pool Dam | Junction with Blackfriars Road | Minor kerbing along with carriageway resurfacing. | 8th July 2024 and 16th August 2024 | Complete
A0520 | 37601023 | Windmill Hill | Meir Heath | Hilderstone Road junction | Roundabout & approaches | Minor kerbing along with carriageway resurfacing. | Between 21st October 2024 and 13th December 2024 | Programmed
| 27000787 | Brook Lane | Newcastle | Stubbs Gate | Friarswood Road | Minor kerbing along with carriageway resurfacing. | Between 2nd September 2024 and 23rd October 2024 | Ongoing
A0522 | 37701263 | Tape Street | Cheadle | Island that serves B5032 Ashbourne Road | Junction area and approaches | Carriageway resurfacing | Between 1st April 2025 and 30th May 2025 | Programmed
B5368 | 27000454 | Lower Milehouse Lane | Cross Heath | Junction of Morrisons Island | Junction area and approaches | Carriageway resurfacing | Between 1st April 2025 and 16th June 2025 | Programmed
A0034 | 37602126 | Queensville Roundabout | Stafford | Island at the junction of Queensville / Silkmore Lane / Ampleforth Drive & access to Quensville retail park | Island at the junction of Queensville / Silkmore Lane / Ampleforth Drive & access to Quensville retail park | Carriageway resurfacing | Between 3rd February 2025 and 9th May 2025 | Programmed
A0034 / A0513 | 37600509 | Weeping Cross Junction | Stafford | Islands at the junction of Radford Bank / Cannock Road / Baswich Lane & Weeping Cross | Islands at the junction of Radford Bank / Cannock Road / Baswich Lane & Weeping Cross | Minor kerbing along with footway and carriageway resurfacing | Between 1st July 2024 and 25th October 2024 | Ongoing
A0034 | 37602359 | Radford Bank | Stafford | Queensville island | Meadow Ridge | Kerbing along with footway and carriageway resurfacing | Between 2nd September 2024 and 17th January 2025 | Ongoing
A0034 | 37600336 | Lichfield Road | Stafford | Riverway | Queensville Avenue | Minor kerbing along with carriageway resurfacing. | Between 5th May 2025 and 27th June 2025 | Programmed
A0511 | 12900175 | Horninglow Street | Burton upon Trent | Guild Street junction |  | Carriageway resurfacing | Between 1st July 2024 and 19th July 2024 | Complete
A0511 / B5008 | 12900064, 12900227 | Swan Junction / Newton Road | Burton upon Trent | Burton Bridge / Ashby Road / Stapenhill Road | Bearwood Hill Road | Carriageway resurfacing | Between 23rd July 2024 and 6th September 2024 | Complete
C0369 | 5500673 | Brownhills Road | Norton Canes | Burntwood Road crossroads | Burntwood Road crossroads | Minor footway & kerbing along with carriageway resurfacing | Between 30th July 2024 and 6th September 2024 | Complete
C0260 | 36701319 | Elliotts Lane / Watery Lane | Codsall | School Entrance | Bilbrook Road | Replacement of high friction surfacing | Between 20th May 2024 and 31st May 2024 | Complete
C0306 (A5127) | 23400231 | Birmingham Road | Lichfield | St.Johns Street | Rotten Row | Carriageway resurfacing | Between 3rd June 2024 and 16th July 2024 | Complete
A0513 | 39400141, 39400477 | Upper Gungate / Aldergate | Tamworth | Combeford Road | Lichfield Street | Carriageway resurfacing | Between 10th February 2025 and 18th April 2025 | Programmed
C0370 | 39400557 | Coton Lane | Tamworth | Combeford Road | Fontenaye Road | Carriageway resurfacing | Between 16th September 2024 and 20th December 2024 | Ongoing
A0449 | 36701766 | Wolverhampton Road | Himley | Crossroads at Dudley Road | Crossroads at Bridgnorth Road | Carriageway resurfacing | Between 27th August 2024 and 20th September | Complete
A0511 | 12900174 | Horninglow Road North | Burton upon Trent | Near Farm Road | Near Calais Road | Minor footway & kerbing along with carriageway resurfacing | Between 13th January 2025 and 14th February 2025 | Programmed
A0515 | 23400268 | Lichfield Road | Wood End, Lichfield | Near Wood End Lane | Railway over bridge | Carriageway resurfacing | Between 10th March 2025 and 31st March 2025 | Programmed
A0034 | 5500612 | Beecroft Road Island | Cannock | Island at the junction of Park Road and Stafford Road | Island at the junction of Park Road and Stafford Road | Carriageway resurfacing | Between 18th April 2024 and 8th May 2024 | Complete
A0460 | 36700471 | Cannock Road / M54 Jct.1 Island | Featherstone | Island that serves A460 and M54 | Island that serves A460 and M54 | Carriageway resurfacing | Between 18th September 2024 and 6th October 2024 September 2024 | Complete
B5017 | 12901232 | Henhurst Hill Crossroads | Burton upon Trent | Hopley Road | Postern Road | Carriageway resurfacing | Between 11th November 2024 and 28th November 2024 | Programmed
B5027 | 12901111 | Stone Road | Uttoxeter | Approx. 70m south Smithfield Road | Approx. 50m west Stone Road and 60m east Stone Road | Carriageway resurfacing | Between 24th February 2025 and 5th March 2025 | Programmed
C0014 | 27000577 | Leycett Lane / Scot Hay Lane | Silverdale | Approx. 115m southeast Kents Lane | Approx. 50m northwest Kents Lane | Carriageway resurfacing | Between 18th November 2024 and 27th November 2024 | Programmed
B5367 | 27001068 | Knutton Lane Link | Newcastle | Knutton Lane | Silverdale Road | Carriageway resurfacing | Between 20th January 2025 and 29th January 2025 | Programmed
D2228 | 27001426 | Gateway Avenue | Baldwins Gate | A53 Newcastle Road | Approx. 165m north of A53 Newcastle Road | Carriageway resurfacing | Between 11th November 2024 and 20th November 2024 | Programmed